## TFG-DalessandroNicolas
UOC TFG: Are-u-Queryous? Web App. - Planning Nicolas Dalessandro Calderon
| Activity | Start date | End date | Linked | February |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  | Comments
[5 empty] | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Project Planning
1.1 | Define project scope and objectives | 2025-02-19 | 2025-02-20 | - | [18 empty] | Completed on-time.- | bar: February W8
1.2 | Research available open geospatial datasets | 2025-02-20 | 2025-02-22 | 1.1 | [18 empty] | Completed on-time.- | bar: February W8
1.3 | Identify key visualization requirements | 2025-02-21 | 2025-02-22 | 1.1 | [18 empty] | Completed on-time.- | bar: February W8
1.4 | Define technology stack and architecture | 2025-02-22 | 2025-02-24 | 1.1., 1.2 | [18 empty] | Completed on-time.- | bar: February W8 to February W9
1.5 | Assess integration challenges | 2025-02-23 | 2025-02-24 | 1.2 | [18 empty] | Completed on-time.- | bar: February W8 to February W9
1.6 | Create detailed project timeline | 2025-02-24 | 2025-02-26 | 1.1, 1.4 | [18 empty] | Completed on-time.- | bar: February W8 to February W9
1.7 | Document sustainability, ethics, and diversity | 2025-02-26 | 2025-02-27 | 1.1 | [18 empty] | Completed on-time.- | bar: February W9
1.8 | Set up development environment | 2025-02-27 | 2025-02-28 | 1.4 | [18 empty] | Completed on-time.- | bar: February W9
1.9 | Compile comprehensive CAT1 documentation | 2025-02-28 | 2025-03-02 | 1.1, 1.8 | [18 empty] | Completed on-time.- | bar: February W9
1.1 | Review and finalize CAT1 documentation | 2025-03-02 | 2025-03-04 | 1.9 | [18 empty] | Succesfully delivered CAT1 under planning.- | bar: February W9 to March W10
2 | Design Phase
2.1 | Define user stories, database schema, and UI wireframes for the mapping interface. | 2025-03-05 | 2025-03-09 | 1.4 | [18 empty] | Completed on-time.- | bar: March W11 to March W12
2.2 | Design system architecture, research filtering algorithms, and create frontend class diagrams. | 2025-03-10 | 2025-03-16 | 2.1 | [18 empty] | Completed on-time.- | bar: March W11 to March W12
2.3 | Develop database documentation, implement login screen, and document state of the art in geospatial data visualization. | 2025-03-17 | 2025-03-23 | 2.1 | [18 empty] | Completed on-time.- | bar: March W12
2.4 | Perfrom State of the Art, Compile and review CAT2 documentation. | 2025-03-23 | 2025-03-31 | 2.1 -2.3 | [18 empty] | Succesfully delivered CAT2 under planning.- | bar: March W11 to March W14
3 | Implementation Phase
3.1 | Set up backend database and implement data ingestion pipelines for open data. | 2025-04-01 | 2025-04-06 | - | [18 empty] | Modified - Changed approach, using Frotend first with Supabase as BaaS for faster deloyment and avoid using Mock data. | bar: April W15 to June W24
3.2 | Develop backend services, authentication, and frontend components for map visualization. | 2025-04-07 | 2025-04-13 | 3.1 | [18 empty] | Completed on-time.- | bar: April W15 to June W24
3.3 | Implement filtering, integrate Leaflet.js, and develop data visualization components. | 2025-04-14 | 2025-04-20 | 3.2 | [18 empty] | Completed Delayed - The frontend implementation was delayed due to different challenges during the development. Succesfully managed to deliver the final project on-time.- | bar: April W16 to June W24
3.4 | Conduct unit testing, perform integration testing, and deploy prototype. | 2025-04-21 | 2025-04-27 | 3.3, 3.4 | [18 empty] | Completed on-time.- | bar: April W18
3.5 | Compile implementation documentation and finalize CAT3 documentation. | 2025-04-27 | 2025-05-05 | 3.1 - 3.4 | [18 empty] | Succesfully delivered CAT3 under planning.- Compiled extensive documentation and prototype for the delivery as well as the Method and Resources for the final Memory. Encountered many issues during development, considering to abrebiate the project. | bar: April W18
4 | Final Product & Report
4.1 | Refine UI based on testing feedback. | 2025-05-07 | 2025-05-11 | 3.14 | May W19: x; May W20: x; May W21: xx; May W22: X; June W23: X; June W24: X | Modified - Feedback loop methodology serves as continuos user testing.-
4.2 | Implement advanced filtering, economic activity visualization, and optimize database queries. | 2025-05-12 | 2025-05-18 | 4.1 | [18 empty] | Completed Delayed - The frontend implementation was delayed due to different challenges during the development. Succesfully managed to deliver the final project on-time.- | bar: May W20 to June W24
4.3 | Fix bugs, optimize performance, and prepare final deployment package. Create user documentation, write results and analysis, draft conclusions, and compile bibliography. | 2025-05-19 | 2025-05-25 | 4.1 | [18 empty] | Completed on-time.- | bar: May W21 to June W24
4.4 | Implement NLP for natural queries (optional) | 2025-05-26 | 2025-06-01 | 4.1 | [18 empty] | Modified - Due to time constrain, the full implementation of this features was not possible. But a UI placeholder was added to be able to simply integrate this service in the near future.- | bar: May W22
4.5 | Finalize and format the project report, then submit CAT4. | 2025-06-01 | 2025-06-03 | 4.1 | [18 empty] | Succesfully delivered CAT4 under planning.- | bar: June W23 to June W24
5 | Presentation
5.1 | Create presentation outline | 2025-06-04 | 2025-06-05 | 4.14 | [18 empty] | Completed on-time.- | bar: June W23
5.2 | Design presentation slides | 2025-06-05 | 2025-06-07 | 5.1 | [18 empty] | Completed on-time.- | bar: June W23 to June W24
5.3 | Prepare demonstration script | 2025-06-06 | 2025-06-07 | 5.1 | [18 empty] | Completed on-time.- | bar: June W24
5.4 | Record demo | 2025-06-07 | 2025-06-08 | 5.2, 5.3 | [18 empty] | Completed on-time.- | bar: June W24
5.5 | Create narrated presentation | 2025-06-08 | 2025-06-09 | 5.2, 5.4 | [18 empty] | Completed on-time.- | bar: June W24
5.6 | Finalize presentation | 2025-06-09 | 2025-06-10 | 5.5 | [18 empty] | Completed on-time.- | bar: June W24