## TFG-DalessandroNicolas
Are u query-ous? Web-App Planning
Activity | Start date | End date | Date | February | [9 empty] | March | [30 empty] | April | [29 empty] | May | [29 empty] | June
|  |  |  | Week 8 |  |  |  |  | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25
 | time axis 2025-02-19 to 2025-06-22
|  |  | Worload | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Planning
Define project scope and objectives | 2025-02-19 | 2025-02-20 | Finished | bar: 2025-02-19 to 2025-02-20
Research available open geospatial datasets | 2025-02-20 | 2025-02-22 | Finished | bar: 2025-02-20 to 2025-02-22
Identify key visualization requirements | 2025-02-21 | 2025-02-22 | Finished | bar: 2025-02-21 to 2025-02-22
Define technology stack and architecture | 2025-02-22 | 2025-02-24 | Finished | bar: 2025-02-22 to 2025-02-24
Assess integration challenges | 2025-02-23 | 2025-02-24 | Finished | bar: 2025-02-23 to 2025-02-24
Create detailed project timeline | 2025-02-24 | 2025-02-26 | Finished | bar: 2025-02-23 to 2025-02-24
Document sustainability, ethics, and diversity | 2025-02-26 | 2025-02-27 | Due Today | bar: 2025-02-26 to 2025-02-27
Set up development environment | 2025-02-27 | 2025-02-28 | 1 | bar: 2025-02-27 to 2025-02-28
Compile comprehensive CAT1 documentation | 2025-02-28 | 2025-03-02 | Not Started | bar: 2025-02-28 to 2025-03-02
Review and finalize CAT1 documentation | 2025-03-02 | 2025-03-04 | Not Started | bar: 2025-03-02 to 2025-03-04
Design Phase
Define user stories and use cases | 2025-03-05 | 2025-03-08 | Not Started | bar: 2025-03-05 to 2025-03-08
Create database schema | 2025-03-08 | 2025-03-11 | Not Started | bar: 2025-03-08 to 2025-03-11
Design UI wireframes | 2025-03-09 | 2025-03-12 | Not Started | bar: 2025-03-09 to 2025-03-12
Design system architecture diagram | 2025-03-12 | 2025-03-14 | Not Started | bar: 2025-03-12 to 2025-03-14
Research filtering algorithms | 2025-03-14 | 2025-03-17 | Not Started | bar: 2025-03-14 to 2025-03-17
Create frontend class diagrams | 2025-03-17 | 2025-03-19 | Not Started | bar: 2025-03-17 to 2025-03-19
Design API endpoints | 2025-03-19 | 2025-03-21 | Not Started | bar: 2025-03-19 to 2025-03-21
Implement login screen prototype | 2025-03-21 | 2025-03-24 | Not Started | bar: 2025-03-21 to 2025-03-24
Implement basic map visualization prototype | 2025-03-24 | 2025-03-28 | Not Started | bar: 2025-03-24 to 2025-03-28
Document state of the art | 2025-03-16 | 2025-03-23 | Not Started | bar: 2025-03-16 to 2025-03-28
Compile and review CAT2 documentation | 2025-03-28 | 2025-04-01 | Not Started | bar: 2025-03-29 to 2025-04-01
Implementation Phase
Set up backend database with PostGIS | 2025-04-02 | 2025-04-04 | Not Started | bar: 2025-04-02 to 2025-04-04
Implement data ingestion pipeline for Barcelona | 2025-04-04 | 2025-04-08 | Not Started | bar: 2025-04-04 to 2025-04-08
Implement data ingestion pipeline for Madrid | 2025-04-08 | 2025-04-12 | Not Started | bar: 2025-04-08 to 2025-04-12
Develop FastAPI backend services | 2025-04-05 | 2025-04-14 | Not Started | bar: 2025-04-05 to 2025-04-14
Implement authentication and user management | 2025-04-14 | 2025-04-17 | Not Started | bar: 2025-04-14 to 2025-04-17
Develop React frontend components | 2025-04-10 | 2025-04-18 | Not Started | bar: 2025-04-10 to 2025-04-18
Implement filtering and querying functionalities | 2025-04-18 | 2025-04-22 | Not Started | bar: 2025-04-18 to 2025-04-22
Integrate Leaflet.js for mapping | 2025-04-22 | 2025-04-25 | Not Started | bar: 2025-04-25 to 2025-04-29
Implement visualization components | 2025-04-25 | 2025-04-29 | Not Started | bar: 2025-04-29 to 2025-05-01
Conduct backend unit testing | 2025-04-29 | 2025-05-01 | Not Started | bar: 2025-05-04 to 2025-05-05
Perform frontend-backend integration testing | 2025-05-01 | 2025-05-04 | Not Started | bar: 2025-05-01 to 2025-05-05
Deploy prototype to development | 2025-05-04 | 2025-05-05 | Not Started | bar: 2025-05-04 to 2025-05-05
Compile implementation documentation | 2025-05-01 | 2025-05-05 | Not Started | bar: 2025-05-01 to 2025-05-05
Review and finalize CAT3 documentation | 2025-05-05 | 2025-05-06 | Not Started | bar: 2025-05-05 to 2025-05-06
Final Product & Report
Refine UI based on feedback | 2025-05-07 | 2025-05-10 | Not Started | bar: 2025-05-07 to 2025-05-10
Implement advanced filtering capabilities | 2025-05-10 | 2025-05-14 | Not Started | bar: 2025-05-10 to 2025-05-14
Add economic visualization features | 2025-05-14 | 2025-05-17 | Not Started | bar: 2025-05-14 to 2025-05-17
Optimize database queries | 2025-05-17 | 2025-05-20 | Not Started | bar: 2025-05-17 to 2025-05-20
Implement NLP for natural queries (optional) | 2025-05-20 | 2025-05-24 | Not Started | bar: 2025-05-20 to 2025-05-24
Conduct system testing | 2025-05-24 | 2025-05-27 | Not Started | bar: 2025-05-24 to 2025-05-27
Fix bugs and performance issues | 2025-05-27 | 2025-05-29 | Not Started | bar: 2025-05-27 to 2025-05-29
Prepare final deployment | 2025-05-29 | 2025-05-30 | Not Started | bar: 2025-05-29 to 2025-05-30
Create user documentation | 2025-05-25 | 2025-05-29 | Not Started | bar: 2025-05-25 to 2025-05-29
Write results and analysis section | 2025-05-15 | 2025-05-25 | Not Started | bar: 2025-05-15 to 2025-05-25
Draft conclusions and future work | 2025-05-25 | 2025-05-28 | Not Started | bar: 2025-05-25 to 2025-05-28
Compile project bibliography | 2025-05-28 | 2025-05-30 | Not Started | bar: 2025-05-28 to 2025-06-01
Finalize complete report | 2025-05-30 | 2025-06-02 | Not Started | bar: 2025-05-30 to 2025-06-03
Review and submit CAT4 | 2025-06-02 | 2025-06-03 | Not Started | bar: 2025-06-02 to 2025-06-03
Presentation
Create presentation outline | 2025-06-04 | 2025-06-05 | Not Started | bar: 2025-06-04 to 2025-06-05
Design presentation slides | 2025-06-05 | 2025-06-07 | Not Started | bar: 2025-06-05 to 2025-06-07
Prepare demonstration script | 2025-06-06 | 2025-06-07 | Not Started | bar: 2025-06-06 to 2025-06-07
Record demo | 2025-06-07 | 2025-06-08 | Not Started | bar: 2025-06-07 to 2025-06-08
Create narrated presentation | 2025-06-08 | 2025-06-09 | Not Started | bar: 2025-06-08 to 2025-06-09
Finalize presentation | 2025-06-09 | 2025-06-10 | Not Started | bar: 2025-06-09 to 2025-06-10
Formulas:
Date = IF([Start date]>TODAY(), "Not Started", IF(TODAY()>[End date], "Finished", IF([End date]=TODAY(), "Due Today", [End date]-TODAY())))