## TFG-DalessandroNicolas
UOC TFG: Are u query-ous? Web-App - Planning Nicolas Dalessandro Calderon
| Activity | Start date | End date | Dependencies | Status | February | [9 empty] | March | [30 empty] | April | [29 empty] | May | [29 empty] | June
[6 empty] | Week 8 |  |  |  |  | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25
 | time axis 2025-02-19 to 2025-06-22
[5 empty] | Worload | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Project Planning
1.1 | Define project scope and objectives | 2025-02-19 | 2025-02-20 | - | Finished | bar: 2025-02-19 to 2025-02-20
1.2 | Research available open geospatial datasets | 2025-02-20 | 2025-02-22 | 1.1 | Finished | bar: 2025-02-20 to 2025-02-22
1.3 | Identify key visualization requirements | 2025-02-21 | 2025-02-22 | 1.1 | Finished | bar: 2025-02-21 to 2025-02-22
1.4 | Define technology stack and architecture | 2025-02-22 | 2025-02-24 | 1.1., 1.2 | Finished | bar: 2025-02-22 to 2025-02-24
1.5 | Assess integration challenges | 2025-02-23 | 2025-02-24 | 1.2 | Finished | bar: 2025-02-23 to 2025-02-24
1.6 | Create detailed project timeline | 2025-02-24 | 2025-02-26 | 1.1, 1.4 | Finished | bar: 2025-02-23 to 2025-02-24
1.7 | Document sustainability, ethics, and diversity | 2025-02-26 | 2025-02-27 | 1.1 | Finished | bar: 2025-02-26 to 2025-02-27
1.8 | Set up development environment | 2025-02-27 | 2025-02-28 | 1.4 | Finished | bar: 2025-02-27 to 2025-02-28
1.9 | Compile comprehensive CAT1 documentation | 2025-02-28 | 2025-03-02 | 1.1, 1.8 | Finished | bar: 2025-02-28 to 2025-03-02
1.1 | Review and finalize CAT1 documentation | 2025-03-02 | 2025-03-04 | 1.9 | 1 | bar: 2025-03-02 to 2025-03-04
2 | Design Phase
2.1 | Define user stories and use cases | 2025-03-05 | 2025-03-08 | 1.1 | Not Started | bar: 2025-03-05 to 2025-03-08
2.2 | Create database schema | 2025-03-08 | 2025-03-11 | 2.1 | Not Started | bar: 2025-03-08 to 2025-03-11
2.3 | Design UI wireframes | 2025-03-09 | 2025-03-12 | 2.1 | Not Started | bar: 2025-03-09 to 2025-03-12
2.4 | Design system architecture diagram | 2025-03-12 | 2025-03-14 | 2.1, 2.2 | Not Started | bar: 2025-03-12 to 2025-03-14
2.5 | Research filtering algorithms | 2025-03-14 | 2025-03-17 | 2.1 | Not Started | bar: 2025-03-14 to 2025-03-17
2.6 | Create frontend class diagrams | 2025-03-17 | 2025-03-19 | 2.3, 2.4 | Not Started | bar: 2025-03-17 to 2025-03-19
2.7 | Design API endpoints | 2025-03-19 | 2025-03-21 | 2.4 | Not Started | bar: 2025-03-19 to 2025-03-21
2.8 | Implement login screen prototype | 2025-03-21 | 2025-03-24 | 2.3, 2.6 | Not Started | bar: 2025-03-21 to 2025-03-24
2.9 | Implement basic map visualization prototype | 2025-03-24 | 2025-03-28 | 2.8 | Not Started | bar: 2025-03-24 to 2025-03-28
2.1 | Document state of the art | 2025-03-16 | 2025-03-23 | - | Not Started | bar: 2025-03-16 to 2025-03-28
2.11 | Compile and review CAT2 documentation | 2025-03-28 | 2025-04-01 | 2.1, 2.10 | Not Started | bar: 2025-03-29 to 2025-04-01
3 | Implementation Phase
3.1 | Set up backend database with PostGIS | 2025-04-02 | 2025-04-04 | 2.11 | Not Started | bar: 2025-04-02 to 2025-04-04
3.2 | Implement data ingestion pipeline for Barcelona | 2025-04-04 | 2025-04-08 | 3.1 | Not Started | bar: 2025-04-04 to 2025-04-08
3.3 | Implement data ingestion pipeline for Madrid | 2025-04-08 | 2025-04-12 | 3.1 | Not Started | bar: 2025-04-08 to 2025-04-12
3.4 | Develop FastAPI backend services | 2025-04-05 | 2025-04-14 | 3.1 | Not Started | bar: 2025-04-05 to 2025-04-14
3.5 | Implement authentication and user management | 2025-04-14 | 2025-04-17 | 3.4 | Not Started | bar: 2025-04-14 to 2025-04-17
3.6 | Develop React frontend components | 2025-04-10 | 2025-04-18 | 2.9 | Not Started | bar: 2025-04-10 to 2025-04-18
3.7 | Implement filtering and querying functionalities | 2025-04-18 | 2025-04-22 | 3.4, 3.6 | Not Started | bar: 2025-04-18 to 2025-04-22
3.8 | Integrate Leaflet.js for mapping | 2025-04-22 | 2025-04-25 | 3.6 | Not Started | bar: 2025-04-25 to 2025-04-29
3.9 | Implement visualization components | 2025-04-25 | 2025-04-29 | 3.6, 3.8 | Not Started | bar: 2025-04-29 to 2025-05-01
3.1 | Conduct backend unit testing | 2025-04-29 | 2025-05-01 | 3.4 | Not Started | bar: 2025-05-04 to 2025-05-05
3.11 | Perform frontend-backend integration testing | 2025-05-01 | 2025-05-04 | 3.6, 3.9 | Not Started | bar: 2025-05-01 to 2025-05-05
3.12 | Deploy prototype to development | 2025-05-04 | 2025-05-05 | 3.10, 3.11 | Not Started | bar: 2025-05-04 to 2025-05-05
3.13 | Compile implementation documentation | 2025-05-01 | 2025-05-05 | 3.1, 3.12 | Not Started | bar: 2025-05-01 to 2025-05-05
3.14 | Review and finalize CAT3 documentation | 2025-05-05 | 2025-05-06 | 3.13 | Not Started | bar: 2025-05-05 to 2025-05-06
4 | Final Product & Report
4.1 | Refine UI based on feedback | 2025-05-07 | 2025-05-10 | 3.14 | Not Started | bar: 2025-05-07 to 2025-05-10
4.2 | Implement advanced filtering capabilities | 2025-05-10 | 2025-05-14 | 4.1 | Not Started | bar: 2025-05-10 to 2025-05-14
4.3 | Add economic visualization features | 2025-05-14 | 2025-05-17 | 4.1 | Not Started | bar: 2025-05-14 to 2025-05-17
4.4 | Optimize database queries | 2025-05-17 | 2025-05-20 | 4.1 | Not Started | bar: 2025-05-17 to 2025-05-20
4.5 | Implement NLP for natural queries (optional) | 2025-05-20 | 2025-05-24 | 4.1 | Not Started | bar: 2025-05-20 to 2025-05-24
4.6 | Conduct system testing | 2025-05-24 | 2025-05-27 | 4.2, 4.5 | Not Started | bar: 2025-05-24 to 2025-05-27
4.7 | Fix bugs and performance issues | 2025-05-27 | 2025-05-29 | 4.6 | Not Started | bar: 2025-05-27 to 2025-05-29
4.8 | Prepare final deployment | 2025-05-29 | 2025-05-30 | 4.7 | Not Started | bar: 2025-05-29 to 2025-05-30
4.9 | Create user documentation | 2025-05-25 | 2025-05-29 | 4.2, 4.5 | Not Started | bar: 2025-05-25 to 2025-05-29
4.1 | Write results and analysis section | 2025-05-15 | 2025-05-25 | - | Not Started | bar: 2025-05-15 to 2025-05-25
4.11 | Draft conclusions and future work | 2025-05-25 | 2025-05-28 | 4.1 | Not Started | bar: 2025-05-25 to 2025-05-28
4.12 | Compile project bibliography | 2025-05-28 | 2025-05-30 | 4.10, 4.11 | Not Started | bar: 2025-05-28 to 2025-06-01
4.13 | Finalize complete report | 2025-05-30 | 2025-06-02 | 4.9, 4.12 | Not Started | bar: 2025-05-30 to 2025-06-03
4.14 | Review and submit CAT4 | 2025-06-02 | 2025-06-03 | 4.8, 4.13 | Not Started | bar: 2025-06-02 to 2025-06-03
5 | Presentation
5.1 | Create presentation outline | 2025-06-04 | 2025-06-05 | 4.14 | Not Started | bar: 2025-06-04 to 2025-06-05
5.2 | Design presentation slides | 2025-06-05 | 2025-06-07 | 5.1 | Not Started | bar: 2025-06-05 to 2025-06-07
5.3 | Prepare demonstration script | 2025-06-06 | 2025-06-07 | 5.1 | Not Started | bar: 2025-06-06 to 2025-06-07
5.4 | Record demo | 2025-06-07 | 2025-06-08 | 5.2, 5.3 | Not Started | bar: 2025-06-07 to 2025-06-08
5.5 | Create narrated presentation | 2025-06-08 | 2025-06-09 | 5.2, 5.4 | Not Started | bar: 2025-06-08 to 2025-06-09
5.6 | Finalize presentation | 2025-06-09 | 2025-06-10 | 5.5 | Not Started | bar: 2025-06-09 to 2025-06-10
Formulas:
Status = IF([Start date]>TODAY(), "Not Started", IF(TODAY()>[End date], "Finished", IF([End date]=TODAY(), "Due Today", [End date]-TODAY())))